## Sheet1
Emotion Recognition system |  | March | March | March | March | April | April | April | April | May | May
Srno | items / Tasks | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
1 | Identify objectives and scope | bar: March Week 1 to March Week 2
2 | Implementation of standard LBP | bar: March Week 3 to April Week 5
3 | Implementation of CNN | bar: April Week 6 to April Week 8
4 | Optimization and hyperparameter tuning | bar: May Week 9 to May Week 10